## Slide 1
DISTINCT
Cross-Network Document Transfer Platform
Development Plan & Delivery Roadmap
.NET 10
RabbitMQ 4.3
PostgreSQL 16
OpenShift
OpenTelemetry
Prepared for Technical Management Review · July 2026

## Slide 2
EXECUTIVE SUMMARY
One platform, five milestones, four people
21
weeks · 4 Program Increments
5
delivery milestones
4
engineers — 2 backend, 1 automation, 1 DevOps
Sprint 3
first end-to-end flow live
Distinct moves documents between two segregated networks through a sanitizing Proxy, converting and splitting files per-format on the way out and reassembling them on the way in. This plan rebuilds the reliability core around a Postgres-native claim / heartbeat / outbox pattern in place of the current Temporal-based POC, proves out the simplest possible end-to-end path first, and then layers in format conversion, per-format autoscaling, VIP prioritization, and full OpenTelemetry observability — with every engineer pairing with Claude Code to keep a four-person team moving on parallel tracks across two networks and a platform layer.
Flagship Milestone 1: a plain .txt file, submitted once, travels Network A → Proxy → Network B and back with zero conversion or splitting logic in the way — proving the reliability core before any transformation complexity is added.
Distinct — Development Plan
2

## Slide 3
V1 SCOPE
What ships first, and what deliberately waits
IN SCOPE FOR V1
✓
Multi-format ingestion, per-format split & convert
✓
Reassembly + reverse-convert in Network B
✓
Per-client folder
✓
VIP-client priority queueing
✓
CSV reporting
✓
OpenTelemetry metrics & distributed tracing
✓
Crash-safe reliability core on OpenShift
OUT OF SCOPE FOR V1
–
End-user facing UI
–
General-purpose logging UI / log search
–
SLA tiers beyond client-provided values
–
Format or feature requirements not yet specified by the client
Distinct — Development Plan
3

## Slide 4
WAY OF WORK
Engineering assumptions that shape how we build
1
Spec-Driven Development (SDD) with BMAD
Every feature starts as a structured spec — requirements, data model, contracts, quickstart — before implementation, worked through the BMAD-METHOD's agent roles (Analyst → PM → Architect → Dev → QA) with Claude Code. Adoption ramps in parallel with the team's existing workflow to manage the learning curve.
2
OpenTelemetry From the First Deliverable
Metrics and traces are wired into Milestone 1's thin slice, not bolted on later. Every subsequent milestone extends the same instrumentation instead of retrofitting it — observability is a day-one requirement, not an afterthought bolted on at go-live.
3
Chaos Testing Is Continuous
Fault-injection and crash-recovery tests run in CI from Milestone 2 onward, not as a one-time validation gate. Every change to the reliability core — claim/heartbeat, sweeper, outbox — is proven against worker crashes before it ships.
4
AI Engineering — Design Through Implementation
Claude Code is used across the full lifecycle, not just as a coding assistant bolted on at the end. Architecture trade-offs, spec authoring, implementation, code review, and test generation all run through the same AI-assisted loop, so design and build stay in lockstep instead of handing off between them.
Distinct — Development Plan
4

## Slide 5
ROADMAP
Five milestones across four Program Increments
M0
Foundations
PI 1 · Wk 1–3
★ FLAGSHIP
M1
E2E Text Flow + Priority & VIP
PI 1-2 · Wk 4–9
M2
Reliability Core
PI 2-3 · Wk 9–15
M3
Conversion & Scaling
PI 3 · Wk 13–18
M4
Observability & Go-Live
PI 3-4 · Wk 17–21
Milestones can overlap by design — reliability hardening (M2) and per-format scaling (M3) share sprint boundaries, and M3 is still finishing as M4 begins. The detailed Gantt on a later slide shows exact task-level dependencies.
Distinct — Development Plan
5

## Slide 6
MILESTONE M1 · WEEKS 4–9 · PI 1–2
Prove the full path end-to-end before adding any transformation complexity
WHAT'S DELIVERED
Ingestion API accepts a job containing plain .txt files
Routing / decision node recognizes “no conversion or split needed” and takes the pass-through path
Reliability Core (claim →complete + transactional outbox) live for this thin slice
Proxy Listener → Assembly → Reverse-Converter (no-op) → Reporting Worker → callback, deployed to OpenShift dev
Priority queue infrastructure in RabbitMQ 4.3
VIP-client tagging end-to-end, from ingestion through reporting
Per-client SLA and timeout ingestion from client-provided configuration
Baseline internal OpenTelemetry metrics and traces across the whole path
SUCCESS CRITERIA / DEMO
A .txt job submitted to Network A is reassembled, reported (CSV), and acknowledged back to Network A.
A VIP job submitted alongside a backlog of standard jobs is processed ahead of the queue, and per-client SLA/timeout values are enforced.
Observability end-to-end in OpenTelemetry.
Demoed live at the Sprint 3 review.
Distinct — Development Plan
6
Outbox Relay hardened for the post-commit-crash path
Mini-manifest-written-before-commit pattern on Network A

## Slide 7
MILESTONE M2 · WEEKS 9–15 · PI 2–3
Make the reliability core survive real failures
WHAT'S DELIVERED
Sweeper service for stale, crashed-worker job recovery
Worker exception framework: transient retries via TTL/DLX, permanent failures via dead queue and DLQ consumers
Mini-manifest-written-before-commit pattern on Network A
Job status rollup (Completed / CompletedPartially / Failed) and a 30-minute timeout sweeper
Chaos test suite that kills workers mid-job and asserts recovery
SUCCESS CRITERIA / DEMO
Killing a worker at any point in the pipeline — mid-claim, post-commit — results in automatic recovery within the design SLAs (~90s via the sweeper, ~500ms via the outbox relay), proven by automated chaos tests running in CI.
Distinct — Development Plan
7

## Slide 8
MILESTONE M3 · WEEKS 13–18 · PI 3
Add real conversion and splitting without letting heavy formats stall fast ones
WHAT'S DELIVERED
Docx, image, and media splitters/converters split out as independent per-format microservices
Per-format horizontal pod autoscaling on OpenShift
Full 5-subflow Proxy Listener: out-of-order chunk/manifest buffering, inline drain, and error sentinels
Per-client folder
Linear-vs-decision-tree routing benchmark with a data-backed recommendation
SUCCESS CRITERIA / DEMO
A mixed batch of PDF, DOCX, image, and media files completes with fast formats unaffected by a backlog of slow ones, and chunk/manifest arrival order is proven not to matter to the outcome.
Distinct — Development Plan
8

## Slide 9
MILESTONE M4 · WEEKS 17–21 · PI 3–4
Production-harden the platform and cut over
WHAT'S DELIVERED
Full OpenTelemetry metrics/traces/logs pipeline with dashboards and alert thresholds
Load and performance testing at target monthly job volume
SUCCESS CRITERIA / DEMO
The platform sustains target monthly job volume within SLA under load test, alerts fire correctly during a DR drill, and UAT is signed off by stakeholders ahead of go-live.
Distinct — Development Plan
9

## Slide 10
DELIVERY ROADMAP
Sprint & PI Gantt — 21 Weeks Across 4 Program Increments
19/7
26/7
2/8
9/8
16/8
23/8
30/8
6/9
13/9
20/9
27/9
4/10
11/10
18/10
25/10
1/11
8/11
15/11
22/11
29/11
6/12
PI 1
PI 2
PI 3
PI 4
Platform / DevOps
Repo, CI & OpenShift Foundations
RabbitMQ 4.3 Topology (DLX/Retry)
Postgres 16 Schema Baseline
OpenTelemetry Skeleton (Collector) + Prometheus
CI/CD Auto-Deploy Pipeline
Priority Queue Infrastructure
Per-Format Autoscaling (HPA)
Observability & DR Hardening
Backend — Network A / Reliability Core
Claim (CAS) Library
Ingestion API + Routing Node
Transactional Outbox + Relay
Per-Client SLA/Timeout Ingestion
VIP Tagging & Priority Routing
Heartbeat Loop + Sweeper (Crash Recovery)
Exception Framework (Retry/DLQ)
Job Rollup + Timeout Sweeper
Backend — Proxy / Network B / File Processing
Proxy Listener Skeleton
Assembly + Reporting + Callback
VIP Priority Handling (Proxy)
Full 5-Subflow Proxy Listener
Per-Format Splitters & Converters
Folder/Schema Preservation
Routing Benchmark (Linear/Tree)
Distributed Tracing (OTel)
Test Automation
Test Harness & Fixtures
E2E Suite — M1 Happy Path
Priority / VIP Validation Suite
Chaos / Fault-Injection Suite
Conversion/Splitting Regression
Load Test Execution & UAT Support
M0
M1 ✓ DEMO
M2
M3
M4 GO-LIVE
1
2
3
4
5
① Postgres schema baseline gates the Reliability Core claim library and later heartbeat/sweeper work (Backend A)
② RabbitMQ topology gates the Outbox Relay and Proxy Listener work (Backend A/B)
③ OpenTelemetry skeleton gates all later per-service instrumentation, through M4
④ Full Proxy Listener depends on Sweeper/Outbox hardening delivered in M2
⑤ Per-format autoscaling depends on the per-format microservice split completing in M3
Distinct — Development Plan
10

## Slide 11
RISKS & MITIGATIONS
What could slow this down, and how we'll handle it
RISK
SEVERITY
MITIGATION
High
High
SDD Learning Curve
Medium
SDD learning and adoption is done in parallel with the “traditional” way of work.
Heavy-format contention if the per-format microservice split slips
Medium
Land the per-format split as the first task of Milestone 3, not the last.
Client-provided inputs (SLA, timeout) arrive late and block M3
Medium
Request formally at kickoff with a named owner and due date; use documented defaults if missed.
Distinct — Development Plan
11